## Sheet3
[6 empty] | SPRINT 1 | [13 empty] | SPRINT 2
GITHUB ISSUE ID | BACKLOG TASK & ID | PRIORITY | ASSIGNED TO | STATUS | SPRINT | 2024-03-17 | 2024-03-18 | 2024-03-19 | 2024-03-20 | 2024-03-21 | 2024-03-22 | 2024-03-23 | 2024-03-24 | 2024-03-25 | 2024-03-26 | 2024-03-27 | 2024-03-28 | 2024-03-29 | 2024-03-30 | 2024-03-31 | 2024-04-01 | 2024-04-02 | 2024-04-03 | 2024-04-04 | 2024-04-05 | 2024-04-06 | 2024-04-07 | 2024-04-08 | 2024-04-09 | 2024-04-10 | 2024-04-11 | 2024-04-12 | 2024-04-13
#2 | As an administrator, i want to be able to authenticate to the app using my login and password in order to use the app | HIGH |  | DONE | 1 | 16.67% | 20% | 33.33% | 55.56% | 61.11% | 77.78% | 88.89% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
| create LOGIN UI |  | BAKHOUCH NISRINE | DONE |  | 50% | 80% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
| create model |  | EL BOUZIYANI ANAS | DONE |  | 0% | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
| create the viewModel |  | EL BOUZIYANI ANAS | DONE |  | 0% | 0% | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
| create service |  | EL BOUZIYANI ANAS | DONE |  | 0% | 0% | 0% | 50% | 50% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
| link firebase project with the application |  | EL BOUZIYANI ANAS | DONE |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
| implement firebase auth logic |  | EL BOUZIYANI ANAS | DONE |  | 0% | 0% | 0% | 0% | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
| implement firebase firestore logic |  | BAKHOUCH NISRINE | DONE |  | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
| test |  | BAKHOUCH NISRINE | DONE |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
| create a theme / color template for the app |  | BAKHOUCH NISRINE | DONE |  | 0% | 0% | 0% | 50% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
#3 | As a user, i want to be able to authenticate to the app using my login and password in order to use the app | HIGH |  | DONE | 1 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
| adapt viewModel |  | EL BOUZIYANI ANAS | DONE |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
| adapt Service |  | EL BOUZIYANI ANAS | DONE |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
| test |  | BAKHOUCH NISRINE | DONE |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
#4 | As a user, i want to be able to register my new account on the app in order to have access | HIGH |  | DONE | 1 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 18.57% | 38.57% | 65.71% | 85.71% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
| create REGISTER UI |  | BAKHOUCH NISRINE | DONE |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 50% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
| adapt viewModel for register |  | EL BOUZIYANI ANAS | DONE |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 80% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
| adapt Service for register |  | EL BOUZIYANI ANAS | DONE |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 50% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
| add register UIState |  | BAKHOUCH NISRINE | DONE |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
| implement navigation logic |  | BAKHOUCH NISRINE | DONE |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 20% | 60% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
| adapt firebase firestore logic |  | EL BOUZIYANI ANAS | DONE |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
| test |  | BAKHOUCH NISRINE | DONE |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
#5 | As a user, i want to be able to reset a my password in order to recover my account to regain access to my lost account | HIGH |  | DONE | 1 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 50% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
| create RESET UI |  | BAKHOUCH NISRINE | DONE |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
| adapt viewModel for reset |  | EL BOUZIYANI ANAS | DONE |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
| adapt Service for reset |  | EL BOUZIYANI ANAS | DONE |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
| add register UIState |  | BAKHOUCH NISRINE | DONE |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
| add reset to navgraph |  | BAKHOUCH NISRINE | DONE |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
| test |  | BAKHOUCH NISRINE | DONE |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
#6 | As an administrator, i want to be able to deactivate a specific user's account in order to deny access to the user | LOW |  | CANCELED | 1 | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
#23 | As a user, I want to see each month's income, expenses, and balance to better understand the situation | HIGH |  | DONE | 2 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 16.67% | 25% | 50% | 66.67% | 83.33% | 87.5% | 91.67% | 100% | 100% | 100% | 100% | 100% | 100%
| set month UI |  | BAKHOUCH NISRINE | DONE |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
| implement models |  | EL BOUZIYANI ANAS | DONE |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
| Understand KotlinFlows and implement them |  | EL BOUZIYANI ANAS | DONE |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 50% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
| set parameters on NavGraph and onClickCallBack on viewmodel |  | BAKHOUCH NISRINE | DONE |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
| implement needed functions on services |  | EL BOUZIYANI ANAS | DONE |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
| debug and test |  | EL BOUZIYANI ANAS | DONE |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 25% | 50% | 100% | 100% | 100% | 100% | 100% | 100%
#24 | As a user, I want to see monthly expenses and income in detail to better understand each month's situation | LOW |  | DONE | 2 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 25% | 25% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 75% | 100% | 100% | 100% | 100%
| implement DetailMonthScreen |  | BAKHOUCH NISRINE | DONE |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
| modify MonthViewModel |  | BAKHOUCH NISRINE | DONE |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
| modify dataService |  | EL BOUZIYANI ANAS | DONE |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 100% | 100% | 100% | 100%
| debug and test |  | EL BOUZIYANI ANAS | DONE |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 100% | 100% | 100%
#8 | as an administrator i want to be able to add new type of expense to the type of expenses predefined on the application in order to manage expenses | LOW |  | IN PROGRESS |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 25% | 25% | 25% | 62.5% | 62.5% | 62.5% | 62.5% | 62.5% | 62.5% | 62.5% | 62.5% | 62.5% | 62.5%
| ste NavDrawer ClickCallBack |  | EL BOUZIYANI ANAS | DONE |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
| Design and code AddExpenseScreen.kt |  | BAKHOUCH NISRINE | DONE |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
| implement viewmodel |  |  | BACKLOG |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| modify services |  |  | IN PROGRESS |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50%
#18 | As an administrator, I want to have the ability to add an expense type to the list of predefined expenses in the app to better categorize expenses | LOW |  | BACKLOG |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
[6 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
#19 | As an administrator, I want to have the ability to edit an expense type from the list of predefined expenses in the app to better categorize expenses | LOW |  | BACKLOG |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
[6 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
#21 | As an administrator, I want to be able to modify an expense among the expenses already recorded in the application in order to fix typos | LOW |  | BACKLOG |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
[6 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
#22 | As an administrator, I want the ability to remove an expense from the expense list to remove incorrect records. | LOW |  | BACKLOG |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
[6 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
#20 | As an administrator, I want to have the ability to add an expense to the expense list by specifying the type, amount, and date (which should be the same day by default) in order to record the expenses. | HIGH |  | BACKLOG | 2 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
[5 empty] | DONE | 2 | 2 | 4 | 5 | 6 | 8 | 9 | 15 | 17 | 19 | 21 | 26 | 30 | 30 | 31 | 33 | 34 | 36 | 38 | 39 | 39 | 39 | 41 | 42 | 44 | 44 | 44 | 44
[5 empty] | IN PROGRESS | 2 | 2 | 1 | 3 | 2 | 1 | 1 | 3 | 3 | 2 | 1 | 1 | 0 | 0 | 1 | 3 | 4 | 3 | 4 | 4 | 5 | 5 | 3 | 3 | 2 | 2 | 2 | 2
[5 empty] | BACKLOG | 52 | 52 | 51 | 48 | 48 | 47 | 46 | 38 | 36 | 35 | 34 | 29 | 26 | 26 | 24 | 20 | 18 | 17 | 14 | 13 | 12 | 12 | 12 | 11 | 10 | 10 | 10 | 10

## Sheet4
| 2024-03-17 | 2024-03-18 | 2024-03-19 | 2024-03-20 | 2024-03-21 | 2024-03-22 | 2024-03-23 | 2024-03-24 | 2024-03-25 | 2024-03-26 | 2024-03-27 | 2024-03-28 | 2024-03-29 | 2024-03-30 | 2024-03-31 | 2024-04-01 | 2024-04-02 | 2024-04-03 | 2024-04-04 | 2024-04-05 | 2024-04-06 | 2024-04-07 | 2024-04-08 | 2024-04-09 | 2024-04-10 | 2024-04-11 | 2024-04-12 | 2024-04-13
DONE | 2 | 2 | 4 | 5 | 6 | 8 | 9 | 15 | 17 | 19 | 21 | 26 | 30 | 30 | 31 | 33 | 34 | 36 | 38 | 39 | 39 | 39 | 41 | 42 | 44 | 44 | 44 | 44
IN PROGRESS | 2 | 2 | 1 | 3 | 2 | 1 | 1 | 3 | 3 | 2 | 1 | 1 | 0 | 0 | 1 | 3 | 4 | 3 | 4 | 4 | 5 | 5 | 3 | 3 | 2 | 2 | 2 | 2
BACKLOG | 52 | 52 | 51 | 48 | 48 | 47 | 46 | 38 | 36 | 35 | 34 | 29 | 26 | 26 | 24 | 20 | 18 | 17 | 14 | 13 | 12 | 12 | 12 | 11 | 10 | 10 | 10 | 10
TOTAL | 2024-03-17: 56
DONE | 2024-03-17: IN PROGRESS; 2024-03-18: BACKLOG
43 | 2024-03-17: 2; 2024-03-18: 6